## A - Final
Item No. | Discription | Units | Unit Price | QTY | Cost
115.1 | DEMOLITION OF BRIDGE NO. S-05-025
995.02 | BRIDGE STRUCTURE NO. S-05-025
BREAK DOWN FOR ITEM 995.02 BRIDGE STRUCTURE NO. S-05-025
| PREFABRICATED TRUSS BRIDGE | LS | 418145.2 | 1 | 420000
910.1 | STEEL REINFORCEMENT FOR STRUCTURES - EPOXY COATED | LB | 4 | 2600 | 11000
903 | 3000 PSI, 1.5 INCH, 565 CEMENT CONCRETE | CY | 440 | 25 | 11000
121.1 | UNCLASSIFIED EXCAVATION | CY | 38 | 130 | 5000
151.1 | GRAVEL BORROW FOR BACKFILLING STRUCTURES | CY | 45 | 120 | 5400
BREAK DOWN FOR ITEM 115.1 DEMOLITION OF BRIDGE NO. S-05-025
181.14 | DISPOSAL OF HAZARDOUS WASTE | TON | 400 | 70 | 28000
| REMOVAL OF EXISTING BRIDGE | LS | 31100 | 1 | 32000
|  |  |  | TOTAL | 512400

## B - Final
Item No. | Discription | Units | Unit Price | QTY | Cost
115.1 | DEMOLITION OF BRIDGE NO. S-05-025
995.02 | BRIDGE STRUCTURE NO. S-05-025
BREAK DOWN FOR ITEM 995.02 BRIDGE STRUCTURE NO. S-05-025
| PREFABRICATED TRUSS BRIDGE | LS | 418145.2 | 1 | 420000
910.1 | STEEL REINFORCEMENT FOR STRUCTURES - EPOXY COATED | LB | 4 | 2600 | 11000
903 | 3000 PSI, 1.5 INCH, 565 CEMENT CONCRETE | CY | 440 | 25 | 11000
121.1 | UNCLASSIFIED EXCAVATION | CY | 38 | 130 | 5000
151.1 | GRAVEL BORROW FOR BACKFILLING STRUCTURES | CY | 45 | 120 | 5400
BREAK DOWN FOR ITEM 115.1 DEMOLITION OF BRIDGE NO. S-05-025
181.14 | DISPOSAL OF HAZARDOUS WASTE | TON | 400 | 70 | 28000
| REMOVAL OF EXISTING BRIDGE | LS | 150000 | 1 | 150000
|  |  |  | TOTAL | 630400

## A - REMOVAL OF EXISTING BRIDGE
Bridge Demolition A
| Unit | Cost | QTY
50' snorkel crane with work platform | DAY | 350 | 3 | 1100
Truck mounted hydraulic boom - 40 ton | DAY | 932 | 3 | 2800
Wood Bridge Demo | SF | 13.6 | 1560 | 22000
|  |  | Total | 25900
|  |  | 20% Contingency | 5200
31100

## B - REMOVAL OF EXISTING BRIDGE
Bridge Demolition B
| Unit | Cost | QTY
40' snorkel crane with work platform | DAY | 294 | 3 | 890
Truck mounted hydraulic boom - 40 ton | DAY | 932 | 3 | 2800
Wood Bridge Demo | SF | 13.6 | 1560 | 22000
Diving crew | DAY | 5000 | 5 | 25000
Pile Removal Crew | DAY | 5500 | 5 | 28000
Dredging | CY | 380 | 120 | 46000
|  |  | SUM | 125000
|  |  | 20% Contingency | 25000
150000

## PREFABRICATED TRUSS BRIDGE
PREFABRICATED TRUSS BRIDGE
| Unit | Cost | QTY
Prefabricated Bowstring Truss Bridge | LS | 375000 | 1 | 375000
Truck mounted hydraulic boom - 40 ton | DAY | 932 | 2 | 1864
Lattice boom crawler crane - 40 ton | DAY | 1179 | 2 | 2358
Front-end loader | DAY | 455 | 2 | 910
|  |  | SUM | 380132
|  |  | 10% Contingency | 38013.2
|  |  | Total | 418145.2

## 151.1
Item No. 151.1 GRAVEL BORROW FOR BACKFILLING STRUCTURES
Backfill is equal to excavation minus concrete
Material | Unit | QTY
Excavation | cy | 130
Concrete | cy | 25
Backfill | cy | 105
SAY | cy | 120

## 121.1
Item No. 120.1 UNCLASSIFIED EXCAVATION (CY)
Excavate existing abuttment walls plus
addition area to pour concrete footings
Per Abutment | Unit | QTY
Height: | ft | 8
Width: | ft | 14
Depth: | ft | 15
Volume: | cy | 62.2222
TOTAL | cy | 124.4444
SAY | cy | 130

## 903
Item No. 903 3000 PSI, 1.5 INCH, 470 CEMENT CONCRETE (CY)
Per Abuttment | Unit | QTY
Stem Height: | ft | 6
Stem Width: | ft | 12
Stem Depth: | ft | 2
Volume: | cy | 5.3333
FTG Height: | ft | 2
FTG Width: | ft | 12
FTG Depth: | ft | 7
Volume: | cy | 6.2222
TOTAL | cy | 23.1111
SAY | cy | 25

## 181.14
Item No. 181.14 DISPOSAL OF HAZARDOUS WASTE (TON)
Members | Length (ft) | QTY | Unit Weight (lb/ft3) | Weight (lb)
Ties | 10 | 80 | 55 | 22000
Piles | 25 | 50 | 55 | 68750
Pile caps | 24 | 10 | 55 | 13200
Girders | 110 | 4 | 55 | 24200
|  | TOTAL | 64.075 | ton
|  | SAY | 70 | ton

## 910.1
Item No. 910.1 STEEL REINFORCEMENT FOR STRUCTURES - EPOXY COATED
Type | length per bar | # of bars | total ft | lb per ft | total lb
#10 footing | 8 | 30 | 240 | 4.3 | 1032
#6 stem | 7 | 24 | 168 | 1.5 | 252
|  |  |  | TOTAL | 2568 | lbs
|  |  |  | SAY | 2600 | lbs

## 181.12
Item No. 181.12 DISPOSAL OF REGULATED SOIL - IN-STATE FACILITY (CY)
Excavated soil is to be used on site for transition
Per Abuttment | Unit | QTY
Height: | ft | 7
Width: | ft | 13
Depth: | ft | 15
Volume: | cy | 101.1111
TOTAL | cy | 101.1111
SAY | cy | 120

## Dredging
Dredging
| Unit | QTY
Depth | ft | 2
Length | ft | 100
Width | ft | 15
TOTAL | 111.1111 | cy
SAY | 120 | cy

## Task List
Mobilisation
Notify local authorities
Clear debrease
Install site fencing and signage
Stage equipment
Receive site trailor
Install debris netting and other environmental mitigation
Demolition Phase
Demo bridge railings
Remove bridge deck
Stage crane
Sawcut piles and girders
hoist decking to staging area for disasembly
Disassemble remove deck material
Install additional bracing to remaining structure
Extract timber piles
Demo abuttment wall
Excavate
Temp shoring
Construction Phase
Formwork + rebar for new abuttments
Pour concrete
Cure concrete
Receive and assemble prefab bridge sections
Install prefab bridge
Install anchor bolts
Touch up structure
Install decking
Demobilisation
Loam and seed impaced areas
Disassemble site fencing and signage
Remove site trailor and equipment