## TimePlan
Sr No | Item | Target Date | Comments | Owner | Status
Administration
1 | Initial Handover | 2009-10-09 | Met with Mayank and got the initial feedback and had initial round of meetings with WPI graduates | VS | Complete
2 | Desk Allocation | 2009-10-26 | Connie allocated 11.558(Dillon) 11.557(Stephen) | VS | Complete
3 | Computers and Phones | 2009-10-26 | Waiting for PC for Dillon. | VS | Complete
4 | Software Installation on PC | 2009-10-30 | Dependent upon 3. Java, Coherence, Eclipse, putty, .Net(Visual Studio 2005) | DB , SM
5 | Admin Rights | 2009-10-30 | Get Admin Rights on PC | DB , SM
Infrastructure
1 | Get Hardware Ready | 2009-10-26 | Got cfj2elxfqa01, njj2elxfqa01, cfj2elxfqa03, pij2elxfqa03 | VS | Complete
2 | Install bWAG | 2009-10-26 | Installed on one machine. Testing and configuring it suitable for the test. Later will replicate to remaining three | VS | Complete
3 | Database | 2009-10-28 | Position and Activity data in Database to load and query | Mayank | Complete
Development
1 | Develop application Objects and initial test code | 2009-10-30 | In Progress | DB, SM | Complete
2 | Work with Cameo + Mayank to get initial development env ready | 2009-10-30 | To decide on POF object names, eclipse project, queries, multi threaded test env, Spring etc | VS | Started
3 | Complete the test case development | 2009-10-30 | Integrate the test environments and finish off the loading and all the querying test cases | DB, SM | Open
Testing
1 | Integration of application and familiarity with Bwag | 2009-10-30 |  | VS,DB,SM | Open
2 | Test Cases Loading 1,2,3 with different Coherence configurations to pick the Optimum | 2009-11-13 |  | DB,SM
3 | Test Case Loading 4 | 2009-11-17
4 | Test Case Querying 1,2,3 | 2009-11-25
4 | Test Case Infra 1,2 | 2009-11-30
5 | Testing .Net | 2009-12-04
6 | Testing WAN | 2009-12-08
Risks
Delay in getting resources for DB,SM
Application Queries
Infrastructure unvavailability
Holidays: Nov 13, Thanksgiving Weekend

## TestCases
Sr No | Test Cases | Expected Results
Loading of Data
1 | Load T-1,T-2 end of day Data ( 1 million, 3 million, 5 million rows) | Time taken
2 | Insert of Realtime data during the day
3 | 40% of realtime data to be inserted to simulate end of day spike
4 | Compare times for updating a NamedCache Vs Loading a new one and deleting the old cache | Strategies whether to update records and insert the missing OR insert the whole set of data and delete the existing RT data/ The better performant strategy would be chosen
5 | Repeat Tests 1-3 in time shifted manner to simulate
three regions
Querying
1 | Query for end of day for a region for a business for an account | Time taken
2 | Compare test times for POFFilter queries and CoherenceSQL queries | Time taken
3 | Query for Real time trade for a region for set of accounts | Strategies for NamedCache whether one per region, or one per region/per business or one per region per business per end of day i.e separate real time and end of day Named Cache.
4 | Query for Position/Activity for Prime Business for one region gor a given trade date/settlement date
5 | Query for Position/Activity for Prime Business for all three regions for a given trade date/settlement date
6 | Get all Trades with status=failed by asset class for today
7 | Get all Trades with status=failed by asset class for T,T-1,T-2
8 | Get all Trades for an account for last 3 days
9 | Load Test: Repeat combination of above querying tets to simulate 50 concurrent users
Load Test: Repeat above Load Test while Test case 4 of Loading of Data
Infrastructure
1 |  | No Data Loss
2 | Crash of Coherence Server while load testing of querying and realtime updates | Time Taken
Crash of Machine while load testing of querying and realtime updates
Time Permitting
Time Taken
1 | .Net Client over WAN connecting to the cluster and querying | Data to be in Sync with cluster
2 | Data Invalidation of Near Cache in .Net Client( over WAN) | Data to be in sync with Active NY cluster
3 | WAN Strategies to have another passive cluster in London | OverHead on NY cluster while load testing

## Environment
Environment
Machines | HP DL360 G5
RAM | 16GB
OS | RedHat AS 4 (Update 6) x86_64
JVM | JRockit 1.6
Item | Number
Cache Server Machines | 8
Client Machines | 2
Cache Servers | 48
Number of Caches | 18
Cache Entries | 1 million per Cache
Total Memory Occupied | 28GB
Size of Activity object | 669 bytes
Size of Position object | 1031 bytes

## Executive Summary
Sr No | Test |  | Time | Notes
1 | Dummy Load
|  | 1 million | 24969ms
|  | 3 million | 74941ms
|  | 5 million | 143951ms
2 | Load 1 million from Database
|  | Without Load | 58521ms
|  | With Load | 341105ms
3 | Query
|  | Primary Key | 1ms | (1 Row Returned)
|  | Settlement Date | 279ms | (147 Rows Returned)
|  | Account Id | 7708ms | (103000 Rows Returned)
Query on Primary key is fastest.
Pagination is a must for rows more than 1000
4 | Strategy1 | Update 40% of rows during peak time | 136025ms
|  | Insert 1 million rows and delete the old Cache | 341120ms
Update of 40% rows is preferrable
5 | Datatype Query | Query on String | 14247ms
|  | Query on Long | 10906ms | Query on Long field is 23.45% faster
6 | Failover | Node failure | 4x spike | 500ms to 2000ms
|  |  | 15s | Oscillating response times
|  | Server failure (6 nodes) | 7x-9x spike
|  |  | 50s | Oscillating response times w/o noise
|  |  | 65s | Oscillating response times w/ noise
o
7 | WAN Replication | Latency | 53ms | Ranges from 50ms - 140ms
|  | Throughput | 110 Object/s | Use delay of 0, batch size of 1000
| Dummy Load | JDBC | JEDI
Positions | 17.258 | 50.04 | 54.194
Activity | 24.582 | 113.358 | 122.668

## Engineering Notes
Lessons Learned
1. Coherence only creates one socket connection for replicating across WAN. The senior member connects to the proxy server.
2. The bottlneck when replicating is Coherence, not WAN connection. (Tested NY-NY)
3. When replicating, should use an asynchonous write behind. Synchronous write causes significant cache delay on NY side.
4. When clearing a cache, there is significant delay in replication. Coherence sends a new event update for each object cleared.
5. 9 Million activites and 9 Million positions are well supported down to 48GB of combined heap space.
6. Failover delay is a spike, not constant.
7. When replicating large amounts of data, push replication 2.3 encounters errors and loses data. Fixed in 2.4, recommend upgrade to 2.5
8. Incoming Buffer Pool size error on proxy server noticed after upgrade to 2.5
9. Each cache needs a publisher. Each publisher opens one socket connection.
Push Replication:
There were couple of major findings with behavior of Push Replication.
1. For the NY cache, it takes about a minute to load about 1 million Postions(rows) into Cache.
With current Push Replication(2.3) turned on in bwag, it takes about 40 minutes! ( almost 40 times overhead).
I believe it introduces some sort of synchronous behavior even though the replication itself is asynchronous it takes about 2-3 hours to flow to London.
Solution --> The new version Push replication 2.5 introduces write behind(asynchronous) to Push replication cache.
This brings down the loading time to around 1.6 minutes ( 60% overhead)
2. As a result of the above, it increases the throughput and on the remote side we see socket buffer overruns and errors pasted below.
Ultimately the socket closes and never reopens.
We tried tuning the pushreplication on the publisher side by lowering the batches and introducing more delay with different settings, JVM settings with maxdirectbuffer, Sun JVM to no avail.
Thanks to NetOps who pointed us in the right direction that the bottleneck is at the proxy server which is a slow consumer and does not dequeue fast enough.
Solution --> Increase the number of threads and more importantly have multiple proxy servers.
This has made it work and so far we were able to replicate about 16 million rows out of 18. Few still have issues which we are looking into.
However you would still see the incoming bufferpool increasing messages which goes upto 20MB rather than the previous 200MB which crashes the proxy server.
Any insight into network, proxy server settings would be welcome.
3. PushRep Publisher : One of the interesting takeaways is there is only one push replication publisher per cache (can be from any nodes)
Translation: Any one member is pushing data to the remote side per cache
4. Proxy server Thread: It is confirmed that even with multiple worker threads, it assigns only one worker thread per incoming socket connection.
Unlike WLS, the daemon thread does not fan out the work amongst its worker threads, but gives a dedicated thread per connection.
5. Clearing Cache: Clearing cache on the master side takes long time. PushRep sends the delete per entry.
It should rather replicate the operation than data.
6. WAN : The bandwidth is allocated along service class(voice, data) and there are sub classifications in that.
By default this goes into the default for data which is the lowest service class capped at 16MB/sec.
Translation -> we could use only 16MB/sec max if no one else is transferring data, but we are sharing that bandwidth across many apps.
However more bandwidth is made available from upper service class in case it is free.
Hence the WAN throughput is elastic.
In our tests between NY and London:
Latency: 53ms
Throughput : 110 Objects/sec
WAN Utilization: 512kbps ( with best PushRep settings of delay=0, batchsize=1000)
Time to replicate 1 million rows: 2.5 hours ( Default Synchronous Push Replication)
7. .Net: .Net clients can connect over WAN to proxy servers and works fine.
The performance of .Net clients and Java clients on PC through proxy server are more or less same.
8. JVM Tests: We also tried different GC settings for Jrockit, and like all GC settings it is highly subjective and dependent on the application.
In the past the default Jrockit GC could not compete with Sun JVM or the gencon. In the newer version, we can see it has
made tremendous progress and outperforms the static gencon GC.
There were few gencon settings that Craig Blitz had sent over from their tests, and that seems to perform better by 20%.
However for our default bwag, I would recommend the default GC for Jrockit as most of the engineering work is being focused on that by both JVMs.
9. JMX Management Node: On both NY and London clusters, we have switch the enterprise manager management node and EM is able to connect to it.
10. CPU: On NY cluster with 6 cache servers on each machine, only during few stress tests, the CPU utilization peaked upto 80%.
Mostly is stays below 40%. No swap.
Network utilization was 20% amongst the NY cluster.

## Tasks
Sr No | Task | Status
1 | Write Junit Test wrapper for all the tests | Done
2 | Create Jmter Ant Script
3 | Create automated script for running tests | Done
4 | Remove implementation of "serializable" interface | Done
5 | Get 40% update data from database | Done
6 | Use PofUpdater as opposed to reflection for Updates | Done
7 | Create a Jedi loader that uses RowMapper | Done
8 | Switch all Pof functions to be of type "String" | Done
9 | Integrate Invocation Service for GC and a class to destroy cache | Done
10 | Load time for 1 mill, 3 mill, 5 mill rows | Done
11 | Baseline Time Taken for each query | Done
12 | Base Time taken with and without Index for Query
13 | Base Line Time taken for queries against database | Done
14 | Baseline times Tests on CF machines Vs Mixe machines
15 | Tests with Caches in one DistributedService Vs DistributedService/Cache | Done
16 | JVM tests | Done
LONG TERM
1 | Add Index Profiler | Not Required
2 | Measure WAN data throughput (Listener in UK) | Done
3 | Address the "Spring batch load problem" | Done
4 | Verify that the whole cluster is Pof-able
5 | Run some of the queries against the database | Done
6 | Address the Date Problem with POF
7 | Add number of threads to service for cache server | Done
8 | Add each cache per service | Done
9 | Dump cache to the file (GREG) | Done

## Summary
|  | Load |  |  |  | Updates (With Noise) |  | Queries (Without Noise) | [7 empty] | Queries (With Noise)
|  | Positions |  | Activities |  | T-New | 40% Update (From db) | Positions |  |  | Activities |  |  |  |  | Positions |  |  | Activities
|  | 9 Million | 1 Million | 9 Million | 1 Million |  |  | Pof Key | BusDate | Accounts | Settlement Date | Accounts & Date | Trade Status (3 Time Zones) | Settlement Date (3 Regions) |  | Pof Key | Date | Accounts | Settlement Date | Accounts & Date | Trade Status (3 Time Zones) | Settlement Date (3 Regions)
Affected Rows |  | 9000000 | 1000000 | 9000000 | 1000000 | 1000000 | 400000 | 103599 | 343909 | 103599 | 147 | 37 | 3000 | 441 |  | 103599 | 343909 | 103599 | 147 | 37 | 3000 | 441
Sequence # | Strategy
1 | Default Policy | 526693 | 58521.4444 | 1031688 | 114632 | 341105 | 136025 | 7551.4 | 22042.575 | 7708.45 | 279.225 | 660.975 | 1057.225 | 556.025 |  | 15598.8718 | 54854.4 | 16311.275 | 516.825 | 1125.675 | 1630.3 | 857.875
2 | Unique Services | 516258 | 57362 | 1033557 | 114839.6667 | 253798.5 | 60945 | 10151.5641 | 21866.359 | 9048.025 | 265.3 | 627.125 | 1040.55 | 561.15 |  | 19313.3333 | 42991.3 | 17511.7 | 563.175 | 1083.7 | 1590.375 | 940.925
3 | Thread Count | 516349.5 | 57372.1667 | 1031624.5 | 114624.9444 | 236713.5 | 79590 | 10055.8 | 22267.1 | 7810.85 | 241.4 | 610.9 | 966.45 | 503.3 |  | 15121.75 | 45529.85 | 19022.8 | 606.05 | 1039.8 | 1719.85 | 803.7
4 | Timeout | 519064.5 | 57673.8333 | 1038381.5 | 115375.7222 | 334160 | 89182 | 7670.7 | 22714.8 | 7981.8 | 292.35 | 693.75 | 1023.2 | 608.55 |  | 13690.35 | 75626.75 | 14147.7 | 462.3 | 992.4 | 1538.35 | 818.85
5 | Default Policy | 514261 | 57140.1111 | 1027465 | 114162.7778 |  |  | 431 | 11639 | 436 | 489 | 642 | 911 | 992 |  | 2037 | 52630 | 2054 | 2243 | 2598 | 3132 | 3136
6 | Deterministic | 479393 | 53265.8889 | 1066235 | 118470.5556 |  |  | 386 | 12408 | 461 | 432 | 572 | 1288 | 1260 |  | 3192 | 45378 | 3144 | 2891 | 3233 | 4286 | 4253
7 | Gencon All | 498330 | 55370 | 1092173 | 121352.5556 |  |  | 478 | 11968 | 458 | 476 | 599 | 980 | 956 |  | 1731 | 40062 | 1689 | 1614 | 1401 | 2367 | 2465
8 | Gencon | 506721 | 56302.3333 | 1109595 | 123288.3333 |  |  | 428 | 14393 | 397 | 473 | 521 | 917 | 951 |  | 2561 | 45771 | 2714 | 2487 | 2852 | 3689 | 3774
9 | Unique Services | 457201 | 50800.1111 | 993138 | 110348.6667 |  |  | 489 | 12163 | 508 | 516 | 627 | 950 | 996 |  | 2044 | 45018 | 1887 | 2119 | 2124 | 3198 | 3322
10 | Unique Services Threaded | 502637 | 55848.5556 | 1094346 | 121594 |  |  | 434 | 12277 | 473 | 507 | 611 | 947 | 996 |  | 1661 | 57043 | 2030 | 1836 | 1903 | 2758 | 2800
11 | Sun JVM | 503032 | 55892.4444 | 1100313 | 122257 |  |  | 329 | 11144 | 338 | 359 | 487 | 752 | 807 |  | 1973 | 40191 | 2115 | 2391 | 2583 | 3029 | 2994
[10 empty] | Activity Trade Status (1000 Rows) | Position Accounts (103599 Rows) | Activity Settlement Date (147 Rows) | Activity Accounts (37 Rows) | Key (1 Row) | Key (1000 Rows)
[9 empty] | Baseline | 492.3 | 458 | 476 | 599 | 1 | 20
[9 empty] | 20 Users | 691.6 | 1689 | 1614 | 1401 | 3 | 36
[9 empty] | Rows Returned | 1000 | 103599 | 147 | 37 | 1 | 1000
|  |  | Query |  | SQL
|  |  | Pof Key |  | SELECT * FROM positions WHERE (accountid=? OR accountid=?) AND region=? AND businessdate=?
|  |  | Position BusDate |  | SELECT * FROM positions WHERE businessdate=? AND region=?
|  |  | Position Accounts |  | SELECT * FROM positions WHERE (accountid=? OR accountid=?) AND region=? AND businessdate=?
|  |  | Activity Settlement Date |  | SELECT * FROM activities WHERE settlementdate=? AND region=?
|  |  | Activity Accounts |  | SELECT * FROM activities WHERE (accountid=? OR accountid=?) AND region=? AND tradedate=?
|  |  | Activity Trade Status 3 Regions |  | SELECT * FROM activities WHERE tradestatus=? AND tradedate =?
|  |  | Activity Settlement Date 3 Regions |  | SELECT * FROM activities WHERE tradedate=? AND settlementdate =?

## Policy Summary
|  | Without Noise |  |  |  | With Noise
Policy | Query Type | Min | Max | Average | Affected Rows | Min | Max | Average | Affected Rows | % Increase
Default Policy
| loadActivityCache | 1010946 | 1010946 | 1010946 | 9000000
| loadPositionCache | 451783 | 451783 | 451783 | 9000000
| strategyOneCreateTable |  |  |  |  | 792501 | 792501 | 792501 | 1000000
| strategyOneDestroyTable |  |  |  |  | 14 | 14 | 14 | 1
| positionPofKey | 345 | 1168 | 516.7 | 914 | 1063 | 2315 | 1560.2 | 914 | 66.88%
| positionDate | 10867 | 19403 | 12596.3 | 343909 | 18930 | 27112 | 22721.5 | 343909 | 44.56%
| positionAccounts | 331 | 548 | 406.7 | 914 | 986 | 2838 | 1444.9 | 914 | 71.85%
| activitySettlementDate | 378 | 688 | 471.1 | 147 | 838 | 2778 | 1575.2 | 147 | 70.09%
| activityTradeDate | 14554 | 16007 | 14998.6 | 360671 | 26462 | 31243 | 28841.2 | 360671 | 48%
| activityTradeStatus | 345 | 555 | 397 | 1000 | 600 | 2517 | 1807.2 | 1000 | 78.03%
| activityAccountsOnDate | 432 | 1120 | 587.9 | 37 | 1160 | 2549 | 1631.7 | 37 | 63.97%
| activityTradeStatus3TimeZones | 851 | 1349 | 1058 | 3000 | 1839 | 2569 | 2271.5 | 3000 | 53.42%
| activitySettlementDate3Regions | 980 | 1766 | 1259.5 | 441 | 1814 | 3202 | 2421.7 | 441 | 47.99%
| percentLoad |  |  |  |  | 302867 | 302867 | 302867 | 400000
Unique Services
| loadActivityCache | 1030005 | 1033755 | 1031880 | 9000000
| loadPositionCache | 515036 | 517219 | 516127.5 | 9000000
| queryActivityAccountsOnDate | 385 | 1044 | 653.1 | 103599 | 544 | 2130 | 1024.85 | 103599 | 36.27%
| queryActivitySettlementDate | 166 | 477 | 275.35 | 147 | 180 | 2405 | 573.25 | 147 | 51.97%
| queryActivitySettlementDate3Regions | 339 | 1186 | 558.55 | 441 | 362 | 7338 | 1056.55 | 441 | 47.13%
| queryActivityTradeStatus3TimeZones | 712 | 1532 | 1040.5 | 3000 | 1037 | 2284 | 1666.15 | 3000 | 37.55%
| queryPositionAccounts | 6700 | 65421 | 10544.5 | 37 | 7041 | 100253 | 20985.35 | 37 | 49.75%
| queryPositionDate | 13259 | 27489 | 21776.25 | 343909 | 22340 | 73289 | 47619.7 | 343909 | 54.27%
| queryPositionPofKey | 5237 | 65814 | 12762.55 | 103599 | 9422 | 83936 | 25510.3 | 103599 | 49.97%
| strategyOneCreateTable | 207646 | 263382 | 235514 |  | 207646 | 325171 | 253798.5 | 1000000
| strategyOneDestroyTable | 15 | 16 | 15.5 |  | 13 | 16 | 14.5 | 1
Thread Count
| loadActivityCache | 1028402 | 1034847 | 1031624.5 | 9000000
| loadPositionCache | 514936 | 517763 | 516349.5 | 9000000
| queryActivityAccountsOnDate | 366 | 952 | 610.9 | 103599 | 630 | 1761 | 1039.8 | 103599 | 41.25%
| queryActivitySettlementDate | 169 | 406 | 241.4 | 147 | 242 | 1106 | 606.05 | 147 | 60.17%
| queryActivitySettlementDate3Regions | 375 | 936 | 503.3 | 441 | 522 | 1129 | 803.7 | 441 | 37.38%
| queryActivityTradeStatus3TimeZones | 684 | 1557 | 966.45 | 3000 | 1155 | 2772 | 1719.85 | 3000 | 43.81%
| queryPositionAccounts | 7066 | 8942 | 7810.85 | 37 | 9612 | 74734 | 19022.8 | 37 | 58.94%
| queryPositionDate | 20633 | 27716 | 22267.1 | 343909 | 31343 | 67986 | 45529.85 | 343909 | 51.09%
| queryPositionPofKey | 6024 | 61846 | 10055.8 | 103599 | 11473 | 24434 | 15121.75 | 103599 | 33.5%
| strategyOneCreateTable |  |  |  |  | 231551 | 241876 | 236713.5 | 1000000
| strategyOneDestroyTable |  |  |  |  | 13 | 16 | 14.5 | 1
Timeout
| loadActivityCache | 1033998 | 1042765 | 1038381.5 | 9000000
| loadPositionCache | 517090 | 521039 | 519064.5 | 9000000
| queryActivityAccountsOnDate | 392 | 1053 | 693.75 | 103599 | 566 | 1687 | 992.4 | 103599 | 30.09%
| queryActivitySettlementDate | 168 | 475 | 292.35 | 147 | 198 | 861 | 462.3 | 147 | 36.76%
| queryActivitySettlementDate3Regions | 384 | 1044 | 608.55 | 441 | 439 | 1418 | 818.85 | 441 | 25.68%
| queryActivityTradeStatus3TimeZones | 706 | 1461 | 1023.2 | 3000 | 1051 | 2079 | 1538.35 | 3000 | 33.49%
| queryPositionAccounts | 6232 | 10039 | 7981.8 | 37 | 11418 | 18790 | 14147.7 | 37 | 43.58%
| queryPositionDate | 20219 | 26933 | 22714.8 | 343909 | 34465 | 750064 | 75626.75 | 343909 | 69.96%
| queryPositionPofKey | 4249 | 12075 | 7670.7 | 103599 | 10903 | 17064 | 13690.35 | 103599 | 43.97%
| strategyOneCreateTable |  |  |  |  | 330447 | 337873 | 334160 | 1000000
| strategyOneDestroyTable |  |  |  |  | 13 | 33 | 23 | 1
Unique Services & Thread Count
| loadActivityCache | 1057224 | 1057224 | 1057224 | 9000000
| loadPositionCache | 465623 | 465623 | 465623 | 9000000
| strategyOneCreateTable |  |  |  |  | 200717 | 200717 | 200717 | 1000000
| strategyOneDestroyTable |  |  |  |  | 139 | 139 | 139 | 1
| positionPofKey | 275 | 927 | 448.3 | 914 | 294 | 2086 | 1039.2 | 914 | 56.86%
| positionDate | 9938 | 13121 | 10760.7 | 343909 | 17607 | 34803 | 27380.6 | 343909 | 60.7%
| positionAccounts | 274 | 1237 | 512.7 | 914 | 346 | 2188 | 1210.7 | 914 | 57.65%
| activitySettlementDate | 423 | 832 | 569 | 147 | 619 | 1786 | 1111.1 | 147 | 48.79%
| activityTradeDate | 13588 | 15877 | 14143.2 | 360671 | 24374 | 50202 | 38211.8 | 360671 | 62.99%
| activityTradeStatus | 317 | 633 | 472.2 | 1000 | 329 | 1734 | 1073.7 | 1000 | 56.02%
| activityAccountsOnDate | 408 | 959 | 593.8 | 37 | 431 | 1933 | 1128.9 | 37 | 47.4%
| activityTradeStatus3TimeZones | 648 | 1384 | 831.4 | 3000 | 906 | 2390 | 1585.5 | 3000 | 47.56%
| activitySettlementDate3Regions | 694 | 1249 | 879 | 441 | 785 | 2145 | 1426.4 | 441 | 38.38%
| percentLoad |  |  |  |  | 80526 | 80526 | 80526 | 400000
Gencon
| loadActivityCache | 1034016 | 1034016 | 1034016 | 9000000
| loadPositionCache | 475450 | 475450 | 475450 | 9000000
| strategyOneCreateTable |  |  |  |  | 533516 | 533516 | 533516 | 1000000
| strategyOneDestroyTable |  |  |  |  | 15 | 15 | 15 | 1
| positionPofKey | 303 | 643 | 389.5 | 914 | 337 | 1512 | 806.2 | 914 | 51.69%
| positionDate | 10800 | 13243 | 11665.6 | 343909 | 21373 | 37468 | 25868.8 | 343909 | 54.9%
| positionAccounts | 363 | 567 | 416.8 | 914 | 495 | 1320 | 856.5 | 914 | 51.34%
| activitySettlementDate | 356 | 712 | 433.6 | 147 | 368 | 1648 | 804.6 | 147 | 46.11%
| activityTradeDate | 14918 | 16448 | 15377.4 | 360671 | 25400 | 47347 | 33958.8 | 360671 | 54.72%
| activityTradeStatus | 381 | 602 | 433.2 | 1000 | 565 | 1610 | 1087 | 1000 | 60.15%
| activityAccountsOnDate | 410 | 656 | 484.6 | 37 | 575 | 1950 | 1231.2 | 37 | 60.64%
| activityTradeStatus3TimeZones | 781 | 1304 | 887.1 | 3000 | 752 | 2399 | 1652.4 | 3000 | 46.31%
| activitySettlementDate3Regions | 806 | 1094 | 897.2 | 441 | 804 | 2556 | 1772.3 | 441 | 49.38%
| percentLoad |  |  |  |  | 103782 | 103782 | 103782 | 400000
Gencon All
| loadActivityCache | 1038505 | 1038505 | 1038505 | 9000000
| loadPositionCache | 474118 | 474118 | 474118 | 9000000
| strategyOneCreateTable |  |  |  |  | 239546 | 239546 | 239546 | 1000000
| strategyOneDestroyTable |  |  |  |  | 31 | 31 | 31 | 1
| positionPofKey | 287 | 742 | 485.8 | 914 | 413 | 1448 | 730.1 | 914 | 33.46%
| positionDate | 9731 | 14769 | 11048.9 | 343909 | 18042 | 20400 | 19543.8 | 343909 | 43.47%
| positionAccounts | 336 | 725 | 468.1 | 914 | 398 | 1136 | 717.5 | 914 | 34.76%
| activitySettlementDate | 391 | 759 | 542.2 | 147 | 495 | 1464 | 1074.3 | 147 | 49.53%
| activityTradeDate | 16163 | 20193 | 17049.3 | 360671 | 22664 | 28064 | 24697.4 | 360671 | 30.97%
| activityTradeStatus | 358 | 797 | 492.3 | 1000 | 503 | 1051 | 691.6 | 1000 | 28.82%
| activityAccountsOnDate | 479 | 840 | 602 | 37 | 875 | 1567 | 1197.9 | 37 | 49.75%
| activityTradeStatus3TimeZones | 754 | 1210 | 912.5 | 3000 | 946 | 2164 | 1437.7 | 3000 | 36.53%
| activitySettlementDate3Regions | 743 | 1484 | 969.5 | 441 | 1243 | 1813 | 1518.1 | 441 | 36.14%
| percentLoad |  |  |  |  | 92815 | 92815 | 92815 | 400000
Sun JVM
| loadActivityCache | 1039735 | 1039735 | 1039735 | 9000000
| loadPositionCache | 470544 | 470544 | 470544 | 9000000
| strategyOneCreateTable |  |  |  |  | 392235 | 392235 | 392235 | 1000000
| strategyOneDestroyTable |  |  |  |  | 5 | 5 | 5 | 1
| positionPofKey | 272 | 2193 | 507.1 | 914 | 914 | 1902 | 1336.3 | 914 | 62.05%
| positionDate | 9558 | 17026 | 10545.1 | 343909 | 17624 | 22889 | 20979 | 343909 | 49.73%
| positionAccounts | 283 | 666 | 348.6 | 914 | 338 | 1165 | 720.2 | 914 | 51.6%
| activitySettlementDate | 313 | 579 | 360.7 | 147 | 327 | 1472 | 988.5 | 147 | 63.51%
| activityTradeDate | 13516 | 14069 | 13691 | 360671 | 23324 | 30149 | 27670.4 | 360671 | 50.52%
| activityTradeStatus | 299 | 439 | 322.6 | 1000 | 640 | 1613 | 985.6 | 1000 | 67.27%
| activityAccountsOnDate | 359 | 674 | 414.9 | 37 | 719 | 1427 | 985.1 | 37 | 57.88%
| activityTradeStatus3TimeZones | 662 | 895 | 728.4 | 3000 | 1436 | 2165 | 1871.5 | 3000 | 61.08%
| activitySettlementDate3Regions | 684 | 918 | 752.4 | 441 | 1253 | 2048 | 1590.6 | 441 | 52.7%
| percentLoad |  |  |  |  | 162669 | 162669 | 162669 | 400000
Deterministic
| loadActivityCache | 1006131 | 1006131 | 1006131 | 9000000 |  |  |  | 9000000
| loadPositionCache | 452278 | 452278 | 452278 | 9000000 |  |  |  | 9000000
| strategyOneCreateTable |  |  |  |  | 709796 | 709796 | 709796 | 1000000
| strategyOneDestroyTable |  |  |  |  | 679 | 679 | 679 | 1
| positionPofKey | 387 | 1120 | 532.2 | 914 | 501 | 2312 | 1350.1 | 914 | 60.58%
| positionDate | 10859 | 13012 | 11505 | 343909 | 20697 | 37141 | 29118.5 | 343909 | 60.49%
| positionAccounts | 332 | 491 | 398.6 | 914 | 489 | 2372 | 1446.3 | 914 | 72.44%
| activitySettlementDate | 370 | 702 | 463.3 | 147 | 355 | 2023 | 1291 | 147 | 64.11%
| activityTradeDate | 14566 | 16031 | 15020.5 | 360671 | 29921 | 47609 | 39604.1 | 360671 | 62.07%
| activityTradeStatus | 363 | 475 | 395.7 | 1000 | 773 | 2350 | 1295.6 | 1000 | 69.46%
| activityAccountsOnDate | 434 | 1135 | 569.3 | 37 | 567 | 2581 | 1505.9 | 37 | 62.2%
| activityTradeStatus3TimeZones | 876 | 1440 | 1043.4 | 3000 | 1373 | 2900 | 1931.8 | 441 | 45.99%
| activitySettlementDate3Regions | 1030 | 1495 | 1287.9 | 441 | 1033 | 3209 | 2324.8 | 1000 | 44.6%
| percentLoad |  |  |  |  | 296471 | 296471 | 296471 | 400000
| Query | SQL
| Pof Key | SELECT * FROM positions WHERE (accountid=? OR accountid=?) AND region=? AND businessdate=?
| Position BusDate | SELECT * FROM positions WHERE businessdate=? AND region=?
| Position Accounts | SELECT * FROM positions WHERE (accountid=? OR accountid=?) AND region=? AND businessdate=?
| Activity Settlement Date | SELECT * FROM activities WHERE settlementdate=? AND region=?
| Activity Accounts | SELECT * FROM activities WHERE (accountid=? OR accountid=?) AND region=? AND tradedate=?
| Activity Trade Status 3 Regions | SELECT * FROM activities WHERE tradestatus=? AND tradedate =?
| Activity Settlement Date 3 Regions | SELECT * FROM activities WHERE tradedate=? AND settlementdate =?

## Query Node Failover
Without Noise |  |  | With Noise
Response Time | Timestamp | T | Response Time | Timestamp | T
415 | 1259603116150 | 0 | 637 | 1259604542865 | 0
644 | 1259603116578 | 0.428 | 1513 | 1259604543516 | 0.651
532 | 1259603117235 | 1.085 | 503 | 1259604545042 | 2.177
430 | 1259603117787 | 1.637 | 1563 | 1259604545560 | 2.695
429 | 1259603118232 | 2.082 | 878 | 1259604547137 | 4.272
361 | 1259603118674 | 2.524 | 1404 | 1259604548030 | 5.165
432 | 1259603119047 | 2.897 | 995 | 1259604549447 | 6.582
325 | 1259603119492 | 3.342 | 1627 | 1259604550457 | 7.592
567 | 1259603119830 | 3.68 | 855 | 1259604552305 | 9.44
807 | 1259603120410 | 4.26 | 1315 | 1259604553183 | 10.318
551 | 1259603121230 | 5.08 | 1433 | 1259604555171 | 12.306
392 | 1259603121794 | 5.644 | 874 | 1259604556918 | 14.053
532 | 1259603122198 | 6.048 | 1064 | 1259604557806 | 14.941
414 | 1259603122744 | 6.594 | 245 | 1259604558884 | 16.019
422 | 1259603123171 | 7.021 | 730 | 1259604564462 | 21.597
431 | 1259603123606 | 7.456 | 617 | 1259604565207 | 22.342
408 | 1259603124051 | 7.901 | 1910 | 1259604565841 | 22.976
384 | 1259603124472 | 8.322 | 344 | 1259604567765 | 24.9
510 | 1259603124868 | 8.718 | 1064 | 1259604568123 | 25.258
434 | 1259603125391 | 9.241 | 1320 | 1259604569204 | 26.339
464 | 1259603125838 | 9.688 | 601 | 1259604570538 | 27.673
342 | 1259603126315 | 10.165 | 1654 | 1259604571154 | 28.289
454 | 1259603126670 | 10.52 | 624 | 1259604572823 | 29.958
533 | 1259603127137 | 10.987 | 444 | 1259604573462 | 30.597
380 | 1259603127683 | 11.533 | 1338 | 1259604573921 | 31.056
594 | 1259603128076 | 11.926 | 920 | 1259604575276 | 32.411
520 | 1259603128686 | 12.536 | 1543 | 1259604576215 | 33.35
427 | 1259603129219 | 13.069 | 906 | 1259604577773 | 34.908
431 | 1259603129659 | 13.509 | 791 | 1259604578693 | 35.828
432 | 1259603130103 | 13.953 | 1581 | 1259604579499 | 36.634
482 | 1259603130548 | 14.398 | 695 | 1259604581095 | 38.23
415 | 1259603131043 | 14.893 | 1172 | 1259604581807 | 38.942
560 | 1259603131471 | 15.321 | 974 | 1259604582993 | 40.128
433 | 1259603132043 | 15.893 | 345 | 1259604583985 | 41.12
402 | 1259603132489 | 16.339 | 1276 | 1259604584345 | 41.48
429 | 1259603132904 | 16.754 | 1113 | 1259604585636 | 42.771
400 | 1259603133346 | 17.196 | 434 | 1259604586765 | 43.9
433 | 1259603133757 | 17.607 | 1485 | 1259604587214 | 44.349
524 | 1259603134202 | 18.052 | 768 | 1259604588713 | 45.848
430 | 1259603134738 | 18.588 | 1575 | 1259604589500 | 46.635
556 | 1259603135180 | 19.03 | 878 | 1259604591105 | 48.24
515 | 1259603135749 | 19.599 | 1386 | 1259604591998 | 49.133
364 | 1259603136280 | 20.13 | 996 | 1259604593398 | 50.533
329 | 1259603136656 | 20.506 | 980 | 1259604594410 | 51.545
426 | 1259603136997 | 20.847 | 1292 | 1259604595403 | 52.538
360 | 1259603137437 | 21.287 | 699 | 1259604596713 | 53.848
538 | 1259603137810 | 21.66 | 1569 | 1259604597426 | 54.561
380 | 1259603138372 | 22.222 | 622 | 1259604599009 | 56.144
405 | 1259603138772 | 22.622 | 1184 | 1259604599645 | 56.78
392 | 1259603139191 | 23.041 | 441 | 1259604600846 | 57.981
511 | 1259603139595 | 23.445 | 1565 | 1259604601300 | 58.435
322 | 1259603140119 | 23.969 | 706 | 1259604602881 | 60.016
493 | 1259603140453 | 24.303 | 1304 | 1259604603601 | 60.736
322 | 1259603140960 | 24.81 | 745 | 1259604604920 | 62.055
612 | 1259603141294 | 25.144 | 1337 | 1259604605679 | 62.814
517 | 1259603141919 | 25.769 | 2056 | 1259604607032 | 64.167
424 | 1259603142450 | 26.3 | 813 | 1259604609107 | 66.242
412 | 1259603142887 | 26.737 | 5141 | 1259604609934 | 67.069
325 | 1259603143312 | 27.162 | 1259 | 1259604615093 | 72.228
420 | 1259603143649 | 27.499 | 1707 | 1259604616411 | 73.546
423 | 1259603144083 | 27.933 | 2078 | 1259604618132 | 75.267
417 | 1259603144519 | 28.369 | 1164 | 1259604620430 | 77.565
504 | 1259603144948 | 28.798 | 1033 | 1259604621648 | 78.783
508 | 1259603145465 | 29.315 | 1127 | 1259604622696 | 79.831
452 | 1259603145986 | 29.836 | 343 | 1259604623839 | 80.974
416 | 1259603146451 | 30.301 | 1073 | 1259604624197 | 81.332
420 | 1259603146880 | 30.73 | 1287 | 1259604625284 | 82.419
422 | 1259603147313 | 31.163 | 415 | 1259604626586 | 83.721
426 | 1259603147748 | 31.598 | 953 | 1259604627016 | 84.151
536 | 1259603148187 | 32.037 | 1140 | 1259604627983 | 85.118
404 | 1259603148736 | 32.586 | 491 | 1259604629137 | 86.272
530 | 1259603149152 | 33.002 | 592 | 1259604629647 | 86.782
342 | 1259603149695 | 33.545 | 1507 | 1259604630253 | 87.388
363 | 1259603150049 | 33.899 | 623 | 1259604631774 | 88.909
411 | 1259603150424 | 34.274 | 932 | 1259604632412 | 89.547
318 | 1259603150848 | 34.698 | 1506 | 1259604633373 | 90.508
424 | 1259603151178 | 35.028 | 729 | 1259604634892 | 92.027
531 | 1259603151615 | 35.465 | 893 | 1259604635636 | 92.771
461 | 1259603152158 | 36.008 | 1348 | 1259604636547 | 93.682
460 | 1259603152632 | 36.482 | 487 | 1259604637914 | 95.049
422 | 1259603153106 | 36.956 | 1476 | 1259604638417 | 95.552
513 | 1259603153541 | 37.391 | 604 | 1259604639909 | 97.044
318 | 1259603154067 | 37.917 | 412 | 1259604640527 | 97.662
359 | 1259603154396 | 38.246 | 1599 | 1259604640953 | 98.088
337 | 1259603154767 | 38.617 | 605 | 1259604642566 | 99.701
459 | 1259603155117 | 38.967 | 1227 | 1259604643185 | 100.32
546 | 1259603155589 | 39.439 | 1126 | 1259604644427 | 101.562
406 | 1259603156148 | 39.998 | 425 | 1259604645568 | 102.703
416 | 1259603156566 | 40.416 | 1164 | 1259604646007 | 103.142
474 | 1259603156995 | 40.845 | 1399 | 1259604647185 | 104.32
395 | 1259603157482 | 41.332 | 815 | 1259604648598 | 105.733
433 | 1259603157890 | 41.74 | 1540 | 1259604649431 | 106.566
553 | 1259603158336 | 42.186 | 742 | 1259604650985 | 108.12
588 | 1259603158910 | 42.76 | 974 | 1259604651741 | 108.876
423 | 1259603159510 | 43.36 | 1310 | 1259604652729 | 109.864
403 | 1259603159946 | 43.796 | 799 | 1259604654054 | 111.189
344 | 1259603160362 | 44.212 | 1252 | 1259604654870 | 112.005
440 | 1259603160718 | 44.568 | 1388 | 1259604656138 | 113.273
318 | 1259603161171 | 45.021 | 1489 | 1259604657541 | 114.676
504 | 1259603161501 | 45.351 | 800 | 1259604659044 | 116.179
2134 | 1259603162020 | 45.87 | 1172 | 1259604659859 | 116.994
611 | 1259603164176 | 48.026 | 1204 | 1259604661045 | 118.18
408 | 1259603164801 | 48.651 | 781 | 1259604662264 | 119.399
582 | 1259603165222 | 49.072 | 1393 | 1259604663059 | 120.194
1442 | 1259603165817 | 49.667 | 1122 | 1259604664467 | 121.602
418 | 1259603167271 | 51.121 | 1245 | 1259604667126 | 124.261
438 | 1259603167702 | 51.552 | 1561 | 1259604668403 | 125.538
1214 | 1259603168152 | 52.002 | 928 | 1259604669990 | 127.125
795 | 1259603169380 | 53.23 | 1008 | 1259604670933 | 128.068
524 | 1259603170188 | 54.038 | 910 | 1259604671955 | 129.09
988 | 1259603170725 | 54.575 | 910 | 1259604672879 | 130.014
430 | 1259603171725 | 55.575 | 2919 | 1259604673803 | 130.938
411 | 1259603172175 | 56.025 | 1054 | 1259604678384 | 135.519
412 | 1259603172599 | 56.449 | 561 | 1259604679453 | 136.588
493 | 1259603173024 | 56.874 | 1852 | 1259604680028 | 137.163
330 | 1259603173530 | 57.38 | 2622 | 1259604681897 | 139.032
858 | 1259603173872 | 57.722 | 546 | 1259604684548 | 141.683
440 | 1259603174743 | 58.593 | 435 | 1259604685107 | 142.242
421 | 1259603175197 | 59.047 | 1601 | 1259604685556 | 142.691
648 | 1259603175631 | 59.481 | 836 | 1259604687171 | 144.306
630 | 1259603176292 | 60.142 | 1236 | 1259604688021 | 145.156
659 | 1259603176935 | 60.785 | 1154 | 1259604689272 | 146.407
460 | 1259603177606 | 61.456 | 982 | 1259604690441 | 147.576
470 | 1259603178079 | 61.929 | 1580 | 1259604691437 | 148.572
489 | 1259603178562 | 62.412 | 1289 | 1259604693030 | 150.165
427 | 1259603179064 | 62.914 | 914 | 1259604694333 | 151.468
342 | 1259603179504 | 63.354 | 751 | 1259604695261 | 152.396
483 | 1259603179870 | 63.72 | 1452 | 1259604696026 | 153.161
484 | 1259603180367 | 64.217 | 972 | 1259604697494 | 154.629
608 | 1259603180863 | 64.713 | 1713 | 1259604698481 | 155.616
521 | 1259603181483 | 65.333 | 822 | 1259604700208 | 157.343
631 | 1259603182018 | 65.868 | 1362 | 1259604701043 | 158.178
499 | 1259603182661 | 66.511 | 1495 | 1259604702421 | 159.556
571 | 1259603183173 | 67.023 | 1893 | 1259604703931 | 161.066
416 | 1259603183757 | 67.607 | 853 | 1259604705838 | 162.973
696 | 1259603184185 | 68.035 | 747 | 1259604706707 | 163.842
444 | 1259603184893 | 68.743 | 1345 | 1259604707479 | 164.614
340 | 1259603185350 | 69.2 | 1101 | 1259604708839 | 165.974
523 | 1259603185702 | 69.552 | 948 | 1259604709964 | 167.099
643 | 1259603186237 | 70.087 | 1446 | 1259604710926 | 168.061
412 | 1259603186893 | 70.743 | 782 | 1259604712386 | 169.521
423 | 1259603187318 | 71.168 | 1277 | 1259604713182 | 170.317
465 | 1259603187754 | 71.604 | 615 | 1259604714472 | 171.607
438 | 1259603188232 | 72.082 | 1010 | 1259604715102 | 172.237
541 | 1259603188683 | 72.533 | 1395 | 1259604716125 | 173.26
332 | 1259603189238 | 73.088 | 679 | 1259604717534 | 174.669
365 | 1259603189582 | 73.432 | 1637 | 1259604718227 | 175.362
511 | 1259603189959 | 73.809 | 661 | 1259604719878 | 177.013
330 | 1259603190491 | 74.341 | 655 | 1259604720553 | 177.688
473 | 1259603190834 | 74.684 | 2188 | 1259604721222 | 178.357
444 | 1259603191319 | 75.169 | 779 | 1259604723438 | 180.573
424 | 1259603191776 | 75.626 | 419 | 1259604724230 | 181.365
484 | 1259603192212 | 76.062 | 1138 | 1259604724662 | 181.797
640 | 1259603192709 | 76.559 |  | 1259604725812 | 182.947
609 | 1259603193362 | 77.212
614 | 1259603193983 | 77.833
478 | 1259603194610 | 78.46
415 | 1259603195100 | 78.95
341 | 1259603195528 | 79.378
412 | 1259603195880 | 79.73
324 | 1259603196305 | 80.155
477 | 1259603196641 | 80.491
501 | 1259603197132 | 80.982
342 | 1259603197649 | 81.499
348 | 1259603198003 | 81.853
411 | 1259603198363 | 82.213
400 | 1259603198787 | 82.637
323 | 1259603199214 | 83.064
437 | 1259603199550 | 83.4
564 | 1259603200000 | 83.85
386 | 1259603200578 | 84.428
398 | 1259603200976 | 84.826
412 | 1259603201386 | 85.236
328 | 1259603201810 | 85.66
426 | 1259603202149 | 85.999

## Query Server Failure
With Noise |  |  | Without Noise
Response Time (ms) | Timestamp | T (seconds) | Response Time (ms) | Timestamp | T (seconds)
839 | 1259606027175 | 0 | 609 | 1259606965397 | 0
559 | 1259606028027 | 0.852 | 410 | 1259606966019 | 0.622
497 | 1259606028601 | 1.426 | 526 | 1259606966442 | 1.045
589 | 1259606029111 | 1.936 | 686 | 1259606966984 | 1.587
1568 | 1259606029714 | 2.539 | 534 | 1259606967683 | 2.286
1135 | 1259606031747 | 4.572 | 1083 | 1259606968230 | 2.833
1511 | 1259606032896 | 5.721 | 834 | 1259606969325 | 3.928
945 | 1259606034646 | 7.471 | 422 | 1259606970172 | 4.775
440 | 1259606035604 | 8.429 | 483 | 1259606970607 | 5.21
1307 | 1259606036056 | 8.881 | 369 | 1259606971104 | 5.707
1151 | 1259606037386 | 10.211 | 1413 | 1259606971485 | 6.088
564 | 1259606038555 | 11.38 | 431 | 1259606972911 | 7.514
2108 | 1259606039132 | 11.957 | 769 | 1259606973355 | 7.958
459 | 1259606043301 | 16.126 | 404 | 1259606974137 | 8.74
347 | 1259606043773 | 16.598 | 435 | 1259606974554 | 9.157
394 | 1259606044131 | 16.956 | 420 | 1259606975004 | 9.607
416 | 1259606044537 | 17.362 | 448 | 1259606975437 | 10.04
418 | 1259606044966 | 17.791 | 503 | 1259606975898 | 10.501
1505 | 1259606045396 | 18.221 | 661 | 1259606976419 | 11.022
1406 | 1259606047363 | 20.188 | 483 | 1259606977093 | 11.696
455 | 1259606048786 | 21.611 | 455 | 1259606977589 | 12.192
417 | 1259606049258 | 22.083 | 404 | 1259606978057 | 12.66
406 | 1259606049687 | 22.512 | 771 | 1259606978475 | 13.078
466 | 1259606050105 | 22.93 | 406 | 1259606979260 | 13.863
2107 | 1259606050588 | 23.413 | 354 | 1259606979679 | 14.282
1867 | 1259606052708 | 25.533 | 407 | 1259606980046 | 14.649
1066 | 1259606054779 | 27.604 | 438 | 1259606980467 | 15.07
494 | 1259606055859 | 28.684 | 398 | 1259606980918 | 15.521
385 | 1259606056366 | 29.191 | 424 | 1259606981329 | 15.932
340 | 1259606056763 | 29.588 | 543 | 1259606981766 | 16.369
376 | 1259606057115 | 29.94 | 407 | 1259606982322 | 16.925
1405 | 1259606057504 | 30.329 | 439 | 1259606982742 | 17.345
1868 | 1259606059189 | 32.014 | 724 | 1259606983205 | 17.808
860 | 1259606061072 | 33.897 | 401 | 1259606983942 | 18.545
1926 | 1259606061951 | 34.776 | 375 | 1259606984356 | 18.959
411 | 1259606063891 | 36.716 | 435 | 1259606984743 | 19.346
539 | 1259606064331 | 37.156 | 455 | 1259606985202 | 19.805
442 | 1259606064883 | 37.708 | 402 | 1259606985670 | 20.273
381 | 1259606065338 | 38.163 | 446 | 1259606986084 | 20.687
789 | 1259606065731 | 38.556 | 375 | 1259606986544 | 21.147
1004 | 1259606066535 | 39.36 | 495 | 1259606986933 | 21.536
4622 | 1259606067554 | 40.379 | 456 | 1259606987441 | 22.044
674 | 1259606072189 | 45.014 | 407 | 1259606987911 | 22.514
5028 | 1259606072876 | 45.701 | 491 | 1259606988339 | 22.942
2344 | 1259606078701 | 51.526 | 638 | 1259606988843 | 23.446
2879 | 1259606081062 | 53.887 | 447 | 1259606989495 | 24.098
2282 | 1259606084245 | 57.07 | 514 | 1259606989955 | 24.558
2275 | 1259606086540 | 59.365 | 499 | 1259606990482 | 25.085
2007 | 1259606089271 | 62.096 | 376 | 1259606990995 | 25.598
1327 | 1259606091307 | 64.132 | 497 | 1259606991393 | 25.996
1360 | 1259606092647 | 65.472 | 405 | 1259606991904 | 26.507
2886 | 1259606094020 | 66.845 | 527 | 1259606992322 | 26.925
2265 | 1259606097416 | 70.241 | 438 | 1259606992863 | 27.466
901 | 1259606099702 | 72.527 | 409 | 1259606993314 | 27.917
1335 | 1259606100616 | 73.441 | 403 | 1259606993736 | 28.339
626 | 1259606101965 | 74.79 | 418 | 1259606994151 | 28.754
666 | 1259606102605 | 75.43 | 458 | 1259606994582 | 29.185
1090 | 1259606103285 | 76.11 | 444 | 1259606995052 | 29.655
2177 | 1259606104393 | 77.218 | 373 | 1259606995509 | 30.112
1141 | 1259606106589 | 79.414 | 476 | 1259606995898 | 30.501
643 | 1259606107744 | 80.569 | 391 | 1259606996388 | 30.991
547 | 1259606108400 | 81.225 | 390 | 1259606996791 | 31.394
554 | 1259606108962 | 81.787 | 541 | 1259606997193 | 31.796
517 | 1259606109531 | 82.356 | 472 | 1259606997747 | 32.35
1747 | 1259606110060 | 82.885 | 476 | 1259606998235 | 32.838
1307 | 1259606112026 | 84.851 | 475 | 1259606998724 | 33.327
831 | 1259606113346 | 86.171 | 802 | 1259606999212 | 33.815
492 | 1259606114190 | 87.015 | 451 | 1259607000027 | 34.63
495 | 1259606114694 | 87.519 | 399 | 1259607000491 | 35.094
1189 | 1259606115205 | 88.03 | 409 | 1259607000902 | 35.505
2845 | 1259606116412 | 89.237 | 470 | 1259607001324 | 35.927
3542 | 1259606119280 | 92.105 | 401 | 1259607001807 | 36.41
938 | 1259606122835 | 95.66 | 421 | 1259607002220 | 36.823
2449 | 1259606123786 | 96.611 | 402 | 1259607002655 | 37.258
1587 | 1259606127013 | 99.838 | 442 | 1259607003069 | 37.672
1265 | 1259606128614 | 101.439 | 474 | 1259607003533 | 38.136
1169 | 1259606129892 | 102.717 | 351 | 1259607004020 | 38.623
406 | 1259606131074 | 103.899 | 405 | 1259607004392 | 38.995
1850 | 1259606131495 | 104.32 | 330 | 1259607004810 | 39.413
1525 | 1259606133359 | 106.184 | 584 | 1259607005153 | 39.756
1612 | 1259606134899 | 107.724 | 319 | 1259607005750 | 40.353
1235 | 1259606136649 | 109.474 | 450 | 1259607006082 | 40.685
465 | 1259606137898 | 110.723 | 481 | 1259607006545 | 41.148
437 | 1259606138376 | 111.201 | 430 | 1259607007038 | 41.641
828 | 1259606138826 | 111.651 | 580 | 1259607007481 | 42.084
1089 | 1259606139666 | 112.491 | 3644 | 1259607008074 | 42.677
1782 | 1259606140777 | 113.602 | 1130 | 1259607011731 | 46.334
1484 | 1259606142775 | 115.6 | 3446 | 1259607012874 | 47.477
671 | 1259606144273 | 117.098 | 2097 | 1259607016334 | 50.937
495 | 1259606144956 | 117.781 | 1111 | 1259607018444 | 53.047
887 | 1259606145465 | 118.29 | 1308 | 1259607019568 | 54.171
1571 | 1259606147804 | 120.629 | 819 | 1259607020889 | 55.492
1240 | 1259606149391 | 122.216 | 462 | 1259607021721 | 56.324
850 | 1259606151138 | 123.963 | 1475 | 1259607022195 | 56.798
424 | 1259606152002 | 124.827 | 1056 | 1259607023683 | 58.286
467 | 1259606152440 | 125.265 | 823 | 1259607024752 | 59.355
1438 | 1259606152920 | 125.745 | 1380 | 1259607025595 | 60.198
1263 | 1259606154962 | 127.787 | 1128 | 1259607026988 | 61.591
708 | 1259606156242 | 129.067 | 1880 | 1259607028129 | 62.732
|  |  | 644 | 1259607030022 | 64.625
|  |  | 626 | 1259607030687 | 65.29
|  |  | 504 | 1259607031326 | 65.929
|  |  | 966 | 1259607031844 | 66.447
|  |  | 751 | 1259607032823 | 67.426
|  |  | 947 | 1259607033587 | 68.19
|  |  | 867 | 1259607034547 | 69.15
|  |  | 900 | 1259607035427 | 70.03
|  |  | 945 | 1259607036340 | 70.943
|  |  | 936 | 1259607037300 | 71.903
|  |  | 5064 | 1259607038249 | 72.852
|  |  | 565 | 1259607043326 | 77.929
|  |  | 665 | 1259607043905 | 78.508
|  |  | 607 | 1259607044585 | 79.188
|  |  | 578 | 1259607045205 | 79.808
|  |  | 931 | 1259607045796 | 80.399
|  |  | 450 | 1259607046740 | 81.343
|  |  | 439 | 1259607047204 | 81.807
|  |  | 711 | 1259607047656 | 82.259
|  |  | 497 | 1259607048391 | 82.994
|  |  | 403 | 1259607048901 | 83.504
|  |  | 983 | 1259607049318 | 83.921
|  |  | 1080 | 1259607050314 | 84.917
|  |  | 586 | 1259607051408 | 86.011
|  |  | 1149 | 1259607052007 | 86.61
|  |  | 485 | 1259607053170 | 87.773
|  |  | 405 | 1259607053668 | 88.271
|  |  | 1134 | 1259607054098 | 88.701
|  |  | 360 | 1259607055246 | 89.849
|  |  | 518 | 1259607055619 | 90.222
|  |  | 840 | 1259607056152 | 90.755
|  |  | 362 | 1259607057006 | 91.609
|  |  | 444 | 1259607057380 | 91.983
|  |  | 454 | 1259607057837 | 92.44
|  |  | 538 | 1259607058309 | 92.912
|  |  | 451 | 1259607058859 | 93.462
|  |  | 418 | 1259607059323 | 93.926
|  |  | 660 | 1259607059754 | 94.357
|  |  | 570 | 1259607060428 | 95.031
|  |  | 426 | 1259607061011 | 95.614
|  |  | 536 | 1259607061450 | 96.053
|  |  | 442 | 1259607061999 | 96.602
|  |  | 421 | 1259607062454 | 97.057
|  |  | 495 | 1259607062889 | 97.492
|  |  | 433 | 1259607063397 | 98
|  |  | 534 | 1259607063843 | 98.446
|  |  | 371 | 1259607064390 | 98.993
|  |  | 631 | 1259607064773 | 99.376
|  |  | 381 | 1259607065417 | 100.02
|  |  | 503 | 1259607065810 | 100.413
|  |  | 546 | 1259607066326 | 100.929
|  |  | 367 | 1259607066885 | 101.488
|  |  | 645 | 1259607067264 | 101.867
|  |  | 429 | 1259607067921 | 102.524
|  |  | 421 | 1259607068363 | 102.966
|  |  | 494 | 1259607068797 | 103.4
|  |  | 565 | 1259607069304 | 103.907
|  |  | 553 | 1259607069886 | 104.489
|  |  | 558 | 1259607070451 | 105.054
|  |  | 425 | 1259607071022 | 105.625
|  |  | 406 | 1259607071461 | 106.064
|  |  | 494 | 1259607071880 | 106.483
|  |  | 355 | 1259607072387 | 106.99
|  |  | 489 | 1259607072754 | 107.357
|  |  | 502 | 1259607073256 | 107.859

## WAN
NYC Load Times
| Batch Size | 1 | 10 | 100 | 1000 | 1 Million w/o replication | 1 min
Delay (ms) | [5 empty] | 1 Million w/ replication | 42 min
0 |  |  | 83 | 100 | 110
250
500
1000 |  |  | 77.6 | 83 | 73
2000
Padding | 1 b | 100b | 1 kb | 10kb | 100kb
Latency | 53ms | 53ms | 58ms | 240ms | 850ms
Range | 50-140ms | 50-140ms | 50-150ms | 180-320ms | 700-1200ms
Batch Size | Delay | Start Time | NY End Time | LDN End Time
10 | 0 | 6:26 | 6:30 | 6:45
100 | 0 | 6:50 | 6:54 | 7:07
1000 | 0 | 7:11 | 7:15 | 7:26
10 | 1000 | 7:30 | 7:34 | 7:51
100 | 1000 | 7:54 | 7:58 | 8:14
1000 | 1000 | 8:16 | 8:20 | 8:39
1 Million Rows |  | 8:40 | 9:22 | 11:57

## .NET
NY -> London
| Query |  | Average
| Activity Acounts On Date |  | 1.987 sec
| Activity Settlement Date |  | 1.993 sec
| Activity Key |  | 275 ms
| Activity Trade Date |  | 2.993 sec
NY->NY
| Activity Acounts On Date |  | 571
| Activity Settlement Date |  | 560
| Activity Key |  | 4.3
Activity Trade Date
Notes
Near Cache only works for keys
|  | Accounts | Settlement Date | Key | Trade Status
| Java | 550 | 500 | 3.5 | 480
| Java via Proxy | 580 | 530 | 4.5 | 500
| .NET via Proxy | 571 | 560 | 4.3 | 496